## Executive Summary
INSPIRE AFRICA GROUP
CONSTRUCTION DEPARTMENT – EXECUTIVE SUMMARY ¦ MAY 2026
Report Date: June 2026 ¦ Total Active Contracts: 135
TOTAL CONTRACTS |  | ✓ COMPLETED |  |  | ▶ ONGOING |  |  | ⚠ HALTED |  |  | ⏸ PAUSED
135 |  | 46 |  |  | 34 |  |  | 32 |  |  | 7
All active work orders |  | 34% of portfolio |  |  | Active execution |  |  | Awaiting resolution |  |  | Temporarily stopped
📊 CONTRACT STATUS OVERVIEW BY CONTRACTOR
Contractor |  | Total Contracts |  | Completed | Ongoing | Halted | Paused | Not Started | Avg Progress
AINEBYOONA ERIC |  | 5 |  | 4 | 0 | 1 | 0 | 0 | 84.0%
ALEX MATWA |  | 8 |  | 5 | 1 | 2 | 0 | 0 | 91.2%
ASIIMWE (MWIMO) |  | 2 |  | 0 | 1 | 0 | 0 | 1 | 47.5%
DOASCORE |  | 4 |  | 2 | 0 | 2 | 0 | 0 | 88.5%
INSPIRE |  | 1 |  | 0 | 1 | 0 | 0 | 0 | 60.0%
JAMES |  | 2 |  | 0 | 2 | 0 | 0 | 0 | 67.5%
JOSIRA ENGINEERING SERVICES |  | 3 |  | 0 | 1 | 0 | 2 | 0 | 54.0%
KAZORA ENGINEERING |  | 6 |  | 2 | 1 | 3 | 0 | 0 | 72.5%
MAKOONA |  | 20 |  | 10 | 0 | 6 | 0 | 4 | 63.0%
MAURICE |  | 3 |  | 1 | 1 | 1 | 0 | 0 | 73.3%
MORIS |  | 3 |  | 1 | 1 | 1 | 0 | 0 | 71.3%
MATOVU ENGINEERING SERVICES |  | 29 |  | 9 | 5 | 7 | 5 | 3 | 66.6%
NEWELL TECHNOLOGIES |  | 9 |  | 0 | 3 | 1 | 0 | 5 | 15.0%
NOWERA |  | 5 |  | 0 | 3 | 2 | 0 | 0 | 0.6%
NUATU |  | 1 |  | 0 | 1 | 0 | 0 | 0 | 70.0%
OCHAYA |  | 12 |  | 6 | 3 | 2 | 0 | 1 | 88.2%
PETER SEGAWA |  | 3 |  | 0 | 2 | 1 | 0 | 0 | 46.7%
PTAKA |  | 2 |  | 0 | 2 | 0 | 0 | 0 | 60.0%
SIGI PATRICK |  | 13 |  | 5 | 4 | 3 | 0 | 1 | 63.7%
TASHOBYA WENS |  | 4 |  | 1 | 2 | 0 | 0 | 1 | 62.5%
BAM |  | 5 |  | 0 | 5 | 0 | 0 | 0 | —
SATE BUILDERS |  | 1 |  | 0 | 1 | 0 | 0 | 0 | 3.0%
TOTAL |  | 135 |  | 46 | 34 | 32 | 7 | 14
⚡ KEY CHALLENGES & RECURRING ISSUES
# | Challenge Category |  | Description |  |  | Contractors Affected |  |  | Priority | Action Points |  | Responsible Person
1 | Payment Delays |  | Multiple contractors report delayed IPC payments affecting remobilisation and material procurement |  |  | Matovu, DOASCORE, Sigi Patrick, PTAKA, Josira, Ochaya, Kazora |  |  | HIGH | 1) Honour reviewed contracts 2) Consultants to expedite review by delegating 3) Finance to set payment schedule |  | Finance / CEO
2 | Material Supply |  | Delayed delivery of hardcore, sand, blocks, culverts and specialised materials stalling progress |  |  | Matovu, Alex Matwa, Newell Technologies, PTAKA, Kazora |  |  | HIGH | 1) Procurement to source alternative suppliers 2) Set weekly material delivery targets 3) Stock critical materials on site |  | Procurement / Logistics
3 | Fleet Management & Availability |  | A number of contractors were affected by the availability and rampant breakdown of fleet, deployment of fleet without consultation of the construction department |  |  | Newell, Doascore, Nowera, Sate, BAM, Matua, Block Making Team |  |  | HIGH | 1) Establish fleet booking system 2) Dedicate equipment to active sites per schedule 3) Set up in-house maintenance team |  | Equipment Manager / PM
4 | Workmanship & Quality |  | Most contractors have demonstrated unsatisfactory workmanship Poor sand deliverec at site |  |  | All contractors |  |  | HIGH | 1) Establish weekly quality meetings, trainings, hire 2 Civil Engineers (Undergraduate one for Nyabihoko and 1 for ACP) to support the technicians on ground 2) Hire competent contrcators 3) Have alternative sources for contractors |  | Procurement /PM
5 | Undefined scope and lack of proper documents |  | Most contracts lack defined scope thus difficult to administer |  |  | All contractors |  |  | HIGH | 1) CEO to intervene 2) Proper contrcats to be authored moving forward |  | CEO/GM//PM
6 | Design Indecision |  | Consultants and clients delaying finishing details, structural drawings and design approvals |  |  | Matovu Engineering (items 1,2,7), DOASCORE, Sigi Patrick |  |  | MEDIUM | 1) Set hard deadlines for design approvals 2) PM to escalate to CEO if unresolved 3) Consultants to provide interim guidance |  | Consultants / PM
7 | Weather Impact |  | Rainy season causing work stoppages, particularly on open-air civil and paving works |  |  | Matovu Engineering, DOASCORE |  |  | MEDIUM | 1) Develop wet-weather work schedule 2) Cover sensitive works with tarpaulins 3) Pre-stock materials ahead of rains |  | Site Engineers / PM
8 | Financial/Value for money |  | Absentia of bidding for projects hence at times awarding contrcats at premium prices with some times overpaying |  |  | Inspire |  |  | MEDIUM | 1) Engineers estimates should be used for benchmarking 2) Bidding protocols should be adopted and a committee setup for award |  | CEO/PM
9 | Equipment Shortage |  | Lack of earthmoving equipment (backhoe, excavator) slowing excavation and trenching activities |  |  | James (Water), Peter Segawa, Newell Technologies |  |  | MEDIUM | 1) Mobilise backhoe and excavator to priority sites 2) Dedicate scheduled days per contractor 3) Explore equipment hire if in-house unavailable |  | Equipment Manager
10 | Safety / Compliance |  | Works halted on cosmetics modification due to PM safety instructions; UETCL pole conflict blocking security house |  |  | Maurice, Matovu (item 26) |  |  | MEDIUM | 1) PM to issue written safety clearance for Maurice 2) Engage UETCL for pole relocation 3) Document safety plan before resumption |  | Project Manager / Engineering
📋 PROJECT MANAGER'S DASHBOARD – JUNE 2026 ACTION ITEMS
Priority |  | Action Required | [6 empty] | Responsible Party |  | Target Date |  | Status
🔴 CRITICAL |  | Release pending IPC payments to all halted contractors (Matovu, DOASCORE, Kazora, PTAKA, Ochaya, Josira) to enable immediate remobilisation | [6 empty] | Finance / Management |  | 10 Jun 2026 |  | PENDING
🔴 CRITICAL |  | Resolve and communicate final finishing design details for Main Gate & LHS perimeter wall (Matovu items 1 & 2) and fountain control room (DOASCORE) | [6 empty] | Consultants / PM |  | 08 Jun 2026 |  | PENDING
🟠 HIGH |  | Procure and deliver hardcore, solid blocks, silt-free sand and culverts to priority sites: Matovu (items 15,20,27), PTAKA, Kazora (items 4,5,6) | [6 empty] | Procurement / Logistics |  | 12 Jun 2026 |  | PENDING
🟠 HIGH |  | Provide structural drawings for Branch-off gate & steel yard wall (Matovu item 7) and resolve UETCL pole conflict blocking security house (item 26) | [6 empty] | Engineering / External |  | 15 Jun 2026 |  | PENDING
🟠 HIGH |  | Mobilise earthmoving equipment (backhoe & excavator) to James water project and Newell Technologies intake chamber — dedicate scheduled days | [6 empty] | Equipment Manager |  | 10 Jun 2026 |  | PENDING
🟡 MEDIUM |  | Approve cosmetics modification safety plan and issue written clearance to Maurice for resumption of erection and sheeting works | [6 empty] | Project Manager |  | 08 Jun 2026 |  | PENDING
🟡 MEDIUM |  | Approve A-shaped units variation for NOWERA and issue outstanding payment for capsules / roofing works to accelerate completion | [6 empty] | PM / Finance |  | 15 Jun 2026 |  | PENDING
🟡 MEDIUM |  | Deliver undelivered lanterns to enable Matovu (item 21) to resume courtyard lantern installation excavation and steel works | [6 empty] | Procurement |  | 14 Jun 2026 |  | PENDING
🟡 MEDIUM |  | Provide facing bricks for Matovu RC shear wall (item 4) and machine for soil spreading at cement store (item 27) | [6 empty] | Procurement / Site |  | 14 Jun 2026 |  | PENDING
🟢 ROUTINE |  | Conduct weekly site progress reviews with all active contractors and update tracker status; escalate new blockers to management | [6 empty] | PM / Site Engineers |  | Every Friday |  | ONGOING
🟢 ROUTINE |  | Monitor NUATU stone crusher retaining wall steel works and coordinate embedded plate delivery to meet July machine installation deadline | [6 empty] | Site Engineer |  | 30 Jun 2026 |  | ONGOING
💰 VERIFIED CONTRACTORS – PAYMENT SUMMARY
S/No | Contractor Name |  |  | Contract Sum (UGX) |  | Amount Paid to Date (UGX) |  | Verified Value Owed (UGX) |  | Consultant Recommendation |  | CEO Approval | Remarks
1 | Talemwa Job |  |  | 165000000 |  | 103000000 |  | 8000000 |  | 8000000 |  | 8000000 | Verified. Approved for payment by Consultant on 09/05/2026
2 | Matovu Vincent Engineering |  |  | 852070000 |  | 265000000 |  | 104069430
3 | Asiimwe Emmy (Mwimos) |  |  | 150000000 |  | 35000000 |  | 10040850
4 | Ainebyona Investments |  |  | 197620000 |  | 95000000 |  | 64188000
5 | Kyambogo Ian – Face Brick Installation |  |  | 22000000 |  | 13000000 |  | -8000 |  |  |  |  | To be given materials to finish works. Value of works done is equivalent to amount paid
6 | Arinaitwe David Kazoora |  |  | 139500000 |  | 88000000 |  | 6408000
7 | Alex Matwa |  |  | 79344600 |  | 40000000 |  | 14485140
8 | Wambogo Samson |  |  | 44000000 |  | 28000000 |  | 2989449
9 | Mubajje Sulah |  |  | 82250000 |  | 23000000 |  | 5067447
24 | Alex Carpenter |  |  | 14000000 |  | 0 |  | 0
10 | Josira Investments |  |  | 130000000 |  | 30000000 |  | 17180848
11 | Segawa Peter |  |  | 24000000 |  | 14000000 |  | 2016000
12 | Omollo Maurice |  |  | 375600000 |  | 140000000 |  | 9508496
TOTAL |  |  |  | 2275384600 |  | 874000000 |  | 243945660
🔧 ENGINEERING & CONSULTANCY WORKS – MAY 2026
Project |  |  | Consultant |  |  | Planned Progress |  | Actual Progress |  | Contract Amount (UGX) |  | Amount Paid (UGX)
Feasibility study for development of a sewer network and wastewater treatment infrastructure |  |  | W.S.T (Dr. Eng. Swaib Semiyaga) |  |  | 60% |  | 50% |  | 200,000,000 |  | 60,000,000
Detailed Hydrological Analysis and Hydraulic Design for storm water Drainage System for the Coffee Airport |  |  | Foldwoc Engineering Company Ltd (Eng. Simon Yiga) |  |  | 50% |  | 18% |  | 70,000,000 |  | 28,000,000
Design of a lakeside resort at Nyabihoko |  |  | Sate Builders Ltd |  |  | 100% |  | 55% |  | TBU |  | TBU
Design of access road to the Airport |  |  | Venture K |  |  | 25% |  | 20% |  | TBU |  | TBU
Quantitative surveying consultancy |  |  | RSU Frank Tebandeke |  |  | TBU |  | TBU |  | TBU |  | TBU
Project Scheduling |  |  | RSU Frank Tebandeke |  |  | TBU |  | TBU |  | TBU |  | TBU
INSPIRE AFRICA GROUP – CONSTRUCTION DEPARTMENT ¦ Confidential ¦ May 2026

## Tracker
INSPIRE AFRICA GROUP – CONSTRUCTION DEPARTMENT ¦ MAY 2026 REPORT & JUNE 2026 OUTLOOK
S/N | Contractor | Contract Details | Contract Amount (UGX) | Variation (UGX) | Received Amount (UGX) | Progress (%) | Status | Current Activity | May 2026 Accomplishments | Challenges | Interventions Required | Planned Completion Date | June 2026 Planned Activities
1 | Matovu Engineering Engineering Services | Perimeter wall and branch off gate to Exhibition | 50,000,000 |  |  | 95% | Halted | perimeter wall snag finishes | 1)Branch off gate finishes100% 2) perimeter wall coping 90% | 1) Soft sand supply and bad weather 2) Traffic control at branch off gate during finishing 3) Delayed payments | 1) Payment 2) Delivery of required material | with in 5 days after commencement | 1) Completion of all remaining finishes and snag rectification
2 | Matovu Engineering Engineering Services | Main Gate and LHS perimeter wall | 50,000,000 | 0 |  | 85% | Halted | coping works on p. wall | 1 Main Gate finishes 97%, 2.perimeter Wall coping 79% | 1) Indecision of finishing details by consultants 2)Delayed payments and bad weather, lack of silt free soft sand for finishes | 1) Payments 2)Remobilisation of workers | 10 days after disbursement of funds | Finish all remaining works and handover
3 | Matovu Engineering Engineering Services | Concrete Road Paving at Exhibition (Phase 1) | 55,000,000 |  |  | 100% | Completed | NA | Finished | 1) Delayed material delivery and inconsistent in water supply | Nil | NA | NA
4 | Matovu Engineering Engineering Services | Rc Shear wall at Exhibition | 30,000,000 |  |  | 95% | Halted | Top coping | On top coping | Delayed installation of facing bricks to pave way for top coping
5 | Matovu Engineering Engineering Services | Drainage System (Culverts and manholes) | 25,000,000 |  |  | 100% | Completed | NA | Finished | Bad weather ( Rainy season)
6 | Matovu Engineering Engineering Services | Kerb stone installation at football pitch | 6,500,000 |  |  | 100% | Completed | NA | Finished | Material supply and delayed payments
7 | Matovu Engineering Engineering Services | Branch-off gate and perimeter Wall Extension at Steel yard | 45,000,000 |  |  | 73% | Halted | shuttering and steel work for gate canopy and wall coping | Shuttering | Delayed structural drawings and design from client
8 | Matovu Engineering Engineering Services | Perimeter wall Extension to Chain link | 5,000,000 |  |  | 97% | Paused | Snag rectification | coping | wall was running within the line of culverts
9 | Matovu Engineering Engineering Services | Concrete Road paving Extension( Phase 2) | 40,000,000 |  |  | 100% | Completed | NA | finished | Levels
10 | Matovu Engineering Engineering Services | stone pitched retaining wall( Entrance to Exhibition) | 10,000,000 |  |  | 100% | Completed | NA | finished | Indecision on levels by the consulting team
11 | Matovu Engineering Engineering Services | Kerb Stone installation ( Main road) | 12,000,000 |  |  | 100% | Completed | NA | finished | Delayed kerb delivery
12 | Matovu Engineering Engineering Services | Walkway Paver laying ( Main road) | 3,500,000 |  |  | 100% | Completed | NA | finished | Bad weather
13 | Matovu Engineering Engineering Services | Concrete Gutter Casting ( Main road) | 3,000,000 |  |  | 100% | Completed | NA | finished | Indecision on the proper design of the gutter
14 | Matovu Engineering Engineering Services | Storage tent platform | 45,000,000 |  |  | 96% | Paused | Screading | concrete works | Stocking of material on the platform
15 | Matovu Engineering Engineering Services | 2 Gates and perimeter wall construction from main gate to drymill | 95,000,000 |  |  | 20% | Halted | plinth wall erection | pads installation and casting | lack of hardcore and solid blocks
16 | Matovu Engineering Engineering Services | Chain link Enclosure at Steel yard | 3,000,000 |  |  | 87% | Paused | concrete chain mashing/ sill | chain installation | Bad weather
17 | Matovu Engineering Engineering Services | Stone pitched retaining wall at storage tent | 8,000,000 |  |  | 42% | Ongoing | Stone pitching works, beams and columns | stone pitching ongoing (69%) | Hard core delivery
18 | Matovu Engineering Engineering Services | Raisers and Separation Wall in Exhibition | 24,070,000 |  |  | 100% | Completed | NA | finished 100% | indecision on the design
19 | Matovu Engineering Engineering Services | Modern toilets, Kitchen and Washrooms at storage tent | 60,000,000 |  |  | 10% | Halted | site clearance | Excess earth clearance | Drawings
20 | Matovu Engineering Engineering Services | Retaining wall btn Exhibition and Storage tent | 25,000,000 |  |  | 0% | Not Started | NA | Nil | Hardcore delivery
21 | Matovu Engineering Engineering Services | Courtyard Lantern installation at selected parts around Exhibition roads | 9,000,000 |  |  | 15% | Halted | Excavation and steel works | 1.column steel erected (100%) 2. All column pads cast(100%) 3. 8 starter columns cast | Un delivered lanterns
22 | Matovu Engineering Engineering Services | Residential units construction at white house | 34,000,000 |  |  | 25% | Ongoing | foundation back fill and compaction | plinth wall | Shared Retaining wall with the cement storage ( residentials have to wait)
23 | Matovu Engineering Engineering Services | Consultancy offices at white house | 16,000,000 |  |  | 78% | Ongoing | beam steel fabrication and formwork | superstructure block walling | Irregular supply of blocks due to consistent machine break down
24 | Matovu Engineering Engineering Services | Agricultural offices at white house | 35,000,000 |  |  | 41% | Ongoing | Block walling | oversite concrete and superstructure block walling | Blocks
25 | Matovu Engineering Engineering Services | Dinning facility at white house | 8,000,000 |  |  | 92% | Ongoing | plasta and finishing | Block walling | Lack of clean silt free soft sand
26 | Matovu Engineering Engineering Services | Security house | 10,000,000 |  |  | 0% | Not Started | NA | Nil | UETCL planted a pole within the house location
27 | Matovu Engineering Engineering Services | Cement Store facility down at white house | 90,000,000 |  |  | 39% | Paused | Back fill and compaction | Retaining wall casting (60%). plinth wall (100%) | Machine to spread soil in preparation for oversite concrete
28 | Matovu Engineering Engineering Services | Extension of dining facility at white house | 15,000,000 |  |  | 0% | Not Started | NA | Nil | Delayed payments to add on man power
29 | Matovu Engineering Engineering Services | Storm water trench at Exhibition | 40,000,000 |  |  | 40% | Paused | wall casting and precast cover slab casting | Base casting and steel works for walls | payments
30 | DOASCORE | Construction of a dancing fountain | 30,000,000 | 0 | 20,000,000 | 100% | Completed |  |  |  | 1) IPC Payment 10M
31 | DOASCORE | Tilling of the fountain | 18,000,000 | 0 | 450,000 | 100% | Completed | Nil | Nil | 1) Indecision of finishing details 2)Indecision on the gate design | 1. IPC payment 17,550,000
32 | DOASCORE | Fountain control room | 15,000,000 |  | 0 | 94% | Halted | Finishing works | Nil | 1) Delayed payments | 1) IPC payment 12M | 10.06.2026 | 1) Floor works 2) Painting works
33 | DOASCORE | Cattle shade 1 Nyabihoko | 60,000,000 |  | 15,000,000 | 60% | Halted | Nil | Nil | 1} Delayed delivery of materials on site | 1) IPC Payment 16M | 15.06.2026 | 1) Back filling 2) Hardcore placing and sand blinding 3) Steel works 4)concrete
34 | SIGI PATRICK | Main gate, Gate to the pitch and Gate to the Administration block | 8,000,000 |  | 4,000,000 | 70% | Ongoing | Gate to the pitch waiting for light and others waiting for cables and light | Piping 70%, Wiring 50%, fittings 35% | 1) lack of materials 2) lack of money to pay workers |  | 8 days after getting materials | 1) laying remaining cables 2) Fitting lights and distribution boards 3) Power supply
35 | SIGI PATRICK | Staff houses 5 rooms | 5,390,000 | 0 | 4,000,000 | 99% | Completed | Handing over | 0.99 | Delayed to pay balance | Paying balance | -
36 | SIGI PATRICK | View point and freeze dry gate | 8,000,000 |  | 4,500,000 | 80% | Ongoing | Waiting for lights | Nil | 1) Indecision on coping design | 1) Coping Design details | 10 days after getting materials | 1) Finishing work after getting materials
37 | SIGI PATRICK | Dry mill and wet mill light | 4,000,000 |  | 2,500,000 | 85% | Halted | Waiting for materials |  | 1) lack of materials 2) lack of money to pay workers |  | 7 days after getting materials | 1) Finishing work after getting materials
38 | SIGI PATRICK | Packaging light, roastry basement light and extraction | 15,000,000 |  | 5,000,000 | 80% | Halted | Waiting for materials |  | 1) lack of materials 2) lack of money to pay workers |  | 14 after getting materials | 1) Finishing work after getting materials
39 | SIGI PATRICK | Museum | 1,000,000 |  | 500,000 | 99% | Completed | Finished |  | Waiting for balance |  | 0 | Handover
40 | SIGI PATRICK | White house/Kawiri's house | 9,000,000 |  | 8,000,000 | 95% | Completed | Finished |  | Waiting for balance |  | 1 day | 1) Finishing work after getting materials
41 | SIGI PATRICK | Slab piping of wood shade | 1,000,000 |  | 0 |  | Completed | Finished |  | Waiting for money |  | 0 | Handover
42 | SIGI PATRICK | Slab piping of dry mill basement | 1,000,000 |  | 0 |  | Completed | Finished |  | Waiting for money |  | 0 | Handover
43 | SIGI PATRICK | Lower cave and upper cave cottages | 30,000,000 |  | 15,000,000 | 65% | Ongoing | Piping remaining cave |  | 1) lack of materials 2) lack of money to pay workers |  | 60 days | Piping remaining cave
44 | SIGI PATRICK | Exhibition tent wiring and 16 sign posts at the pitch | 15,000,000 |  | 5,000,000 | 65% | Ongoing | Waiting for materials |  | 1) lack of materials 2) lack of money to pay workers |  | 14 days
45 | SIGI PATRICK | Administration block | 35,000,000 |  | 13,000,000 | 90% | Halted | - |  | 1) lack of materials 2) lack of money to pay workers
46 | SIGI PATRICK | Addition works in lower and upper cave cottages | 15,000,000 |  | 0 | 0% | Not Started | - |  | 1) lack of materials 2) lack of money to pay workers |  | 90 days
47 | ALEX MATWA | Cosmetic |  | 0 | 10m | 60% | Ongoing | Finishing slab |  | change of design, delay of materials, transports material for himself | aggregates,sand,and blocks(0.2x0.4)cm3 | 15/06/2026 | plastering, block work completioin, formwork completion.
48 | ALEX MATWA | LPG(tank base) |  | 0 | 10m | 85% | Halted | Nil | Nil | money, material | sand, aggregates | 15/06/2026 | completion of the work
49 | ALEX MATWA | ramp behind cold brew |  |  | 1m | 85% | Halted | NIL | Nil | Money and material | sand and aggregates | 20/06/2026 | completion of the work
50 | ALEX MATWA | Boiler chamber |  |  | 0 | 100% | Completed | Nil | Nil | money demand
51 | ALEX MATWA | PARTION WALL INSIDE COSMETICS |  |  |  | 100% | Completed |  |  | money demand
52 | ALEX MATWA | POWER HOUSE AT THE DAM AREA |  |  |  | 100% | Completed |  |  | money demand
53 | ALEX MATWA | Stone pitching behind cosmetics |  |  | 5m | 100% | Completed |  |  | money demand
54 | ALEX MATWA | Retaining wall behind power house |  |  | 5m | 100% | Completed |  |  | money demand
55 | MORIS | Cosmetics roofing and fabrication |  | 0 |  | 20% | Halted | erected 1 truss, fabrication completed |  | completion of slab |  |  | completion of trusses and roofing
56 | MORIS | POWER HOUSE |  | 0 |  | 100% | Completed | FINISHED FABRICATION OF PLATES | Nil |  |  |  | COMPLETED
57 | MORIS | EXHIBITION TENT | 0 |  | 0 | 94% | Ongoing | Tent installation and fabrication | Nil | 1) Delayed payments | sealant |  | completion of tent installation
58 | PETER SEGAWA | Casting topslab at the power house |  | 0 |  | 50% | Ongoing | making formwork |  | money, material | sand, aggregates |  | casting of the slab
59 | PETER SEGAWA | Drainage channel behind Extraction |  | 0 |  | 40% | Ongoing | Nil | Nil | material and money |  |  | completion of the drainage channel
60 | PETER SEGAWA | required to determine levels |  |  | 0 | 50% | Halted |  | Nil | change in levels
61 | TASHOBYA WENS | Construction of the gates | 70,000,000 | 2,000,000 | 35,000,000 | 70% | Ongoing | Ring beam shuttering and steel works | 1) casting ring beam 70% plastering 50% | 1) delays in material delivery (2) Delayed payments | 1) IPC Payment 1M 2) Approval of the Variation | 25.06.2026 | 1) Completion of the Ring beam 2) Plastering and rendering
62 | TASHOBYA WENS | retaining wall, car ramp, perimeter wall
63 | TASHOBYA WENS | CAR parking,perimeter wall and kerbstone | 35,000,000 | 0 | 15,000,000 | 80% | Ongoing | plastering and Rendering |  | 1) Indecision of finishing details | 1) Finishing details 2)Partial payment | 15.06.2026 | plastering and copings
64 | TASHOBYA WENS | construction of stone masonry drai,culvert installation and pavement | 25,000,000 | N/A | 10,000,000 | 100% | Completed | Nil | Nil
65 | MAURICE | Power House/Mezzanine Floor | 5,000,000 | 0 | NIL | 100% | Completed | N/A | N/A | NONE | N/A | N/A | N/A
66 | MAURICE | Exhibition Works | 35,000,000 | 0 | 10,000,000 | 90% | Ongoing | Silicon filling | Nil | 1)Payments delay | 1) passage tent need to be checked and approved before we proceed | 10.06.2026 | 1) Completion of works at Exhibition
67 | MAURICE | Cosmetic Modification | 20,000,000 | 0 | 5,000,000 | 30% | Halted | Non | Nil | 1)Works were halted due to safety precautions that were instructed by the project manager | 1) Resumption of works | N/A | 1) Continuation of erection and sheeting of the laboratory
68 | ASIIMWE (MWIMO) | CONSTRUCTION OF RETAINING WALL | 65,000,000 | NO | 28,000,000 | 95% | Ongoing | SHUTTERING AND FORMWORK FOR CONCRETE | 1) STEEL WORKS 100% 2) CONCRETE CASTING OF THE WALL 95% | WATER TREATMENT 95% | 05.06.2026 |  | 1) Inspire 2) Inspire
69 | ASIIMWE (MWIMO) | CONSTRUCTION OF WETMILL | 85,000,000 | 0 | KL |  | Pending Site Location
70 | PTAKA | construction of retaining wall and repairing the storm water drainage channel at link 1 & link 7 roads | 144,275,000 |  | 35,000,000 | 70% | Ongoing | desilting,removing debris from existing drain | 1) desilting done 20% | 1) inadequate labour 2) material (hardcore) 3) Delayed payments | payment | 30.06.2026 | 1) working on drainage channel repair, base and walls link 1
71 | PTAKA | Concrete U drain, access culverts and end structures for cross Culvert at link 7 | 50,000,000 |  | 0 | 50% | Ongoing | concerts for u drain base and walls, steel work for u drain and end structures | 1).Access culverts 80%, 2).concrete u drain 65%, 3).end structures 10% | delayed payments | payments | 15.06.2026 | 1) complete concrete u drain 2) complete culvert installation for access 3) complete end structures (manholes)
72 | OCHAYA | Installation of the curtain wall at exhibition tent | 30,000,000 |  |  | 95% | Ongoing | fixing the curtain wall frames | installation of the curtain wall frames | plumbing works to help in work progress | 1) IPC Payment | Nil | nil
73 | OCHAYA | Administration gate cladding works | 20,000,000 | 0 | 5,000,000 | 100% | Completed |  |  | IPC payment
74 | OCHAYA | Store 1 cladding works. | 123,000,000 |  | 98,000,000 | 85% | Ongoing | cladding fixing and frames assembling | finished cladding works | ,IPC payment
75 | OCHAYA | packaging cladding works and glass partition | 6,000,000 |  | 4,000,000 | 100% | Completed |  | cladding works and glass partition in packaging | IPC payment |  |  | fixing iron sheets
76 | OCHAYA | Cosmetics cladding | 80,000,000 |  | 40,000,000 | 85% | Ongoing | panel cladding | remaining to to fix ironsheets | IPC payment
77 | OCHAYA | Roastrty Lab area glass roof | 12,000,000 |  | 2,000,000 | 100% | Completed |  | installation of the yellow panels and aluminium partition for the lab area | ,IPC payment
78 | OCHAYA | canopy front roastry | 4,000,000 |  |  | 100% | Completed |  |  | ,IPC payment
79 | OCHAYA | Cladding inside the roastry | 6,000,000 |  | 4,000,000 | 100% | Completed |  |  | IPC payment
80 | OCHAYA | cladding and glass partition coffee shop | 9,000,000 |  | 4,000,000 | 100% | Completed |  |  | IPC payment
81 | OCHAYA | Cladding for the fountain power house | 3,000,000 |  |  | 95% | Halted |  | installation of the panels | IPC payment
82 | OCHAYA | Office block and wetmill cladding | 22,000,000 |  |  | 98% | Halted |  | installation of the yellow panels and aluminium partition for the wetmill | IPC payment
83 | OCHAYA | Freeze dry ramp cladding | 20,000,000 |  | no payment recieved | 0% | Not Started |  |  | IPC payment
84 | KAZORA ENGINEERING | Stone masonry work below link 2 below dispatch. 3000m | 32,000,000 | 0 | 30,000,000 | 100% | Completed
85 | KAZORA ENGINEERING | Finishing masonry wall(stone pointing) | 35,000,000 | 0 | 28,000,000 | 100% | Completed
86 | KAZORA ENGINEERING | Fixing culvertsand casting 3 manholes near cement store. | 15,000,000 |  | 10,000,000 | 85% | Ongoing | casting manholes | fixing culverts and casting,casting manholes, | adequate murram,IPC payment |  | 14/06/2026 | making manhole covers ,backfilling.
87 | KAZORA ENGINEERING | Building edges ,store leveling,fixing culverts,casting edges with retaining wall(CEO residence) | 17,000,000 |  | 10,000,000 | 75% | Halted |  |  | culverts,IPC payment |  | 20/06/2026
88 | KAZORA ENGINEERING | Fixing culverts and 4 manhole covers in NYABIHOKO | 12,000,000 |  | 0 | 60% | Halted |  |  | missing culverts,aggregate,sand |  | 28/06/2026 | building headwalls,fixing culverts.
89 | KAZORA ENGINEERING | Stone pitching and curbstones,near cement store. | 28,500,000 |  | 0 | 15% | Halted |  |  | hardcore,IPC payment |  | 20/07/2026 | stone pitching
90 | JOSIRA ENGINEERING SERVICES. | Construction of concrete U drain at ring road 1 (375m) | 130,000,000 | 0 | 30,000,000 | 90% | Ongoing | Casting concrete for base and side walls | Nil | Delayed payments, Delay in material delivery | 1) IPC Payment of 60M | 2nd June 2026 | casting concrete for base and side walls on the remaining 10%
91 | JOSIRA ENGINEERING SERVICES. | Stone pitching U drain from academy to Helipad road(305m) |  | 0 |  | 60% | Paused | Nil | Nil | Delayed material supply of hard core |  | 17th June 2026 | Stone pitching embarkment and back slope walls and casting base
92 | JOSIRA ENGINEERING SERVICES. | Construction of concrete drainage at left hand side and stone pitching drainage at right hand side at CEO road |  |  |  | 12% | Paused | Nil | Nil | 1) Delayed payments |  | 2nd July 2026 | excavations, blinding, formwork, Stone pitching work and casting concrete
93 | AINEBYOONA ERIC | 514 GABION BOXES OF (2X1X1) INSTALLATION AT THE TANK HILL INCLUDING TRANSPORTATION OF HARD CORE FROM NYABIHOKO | 61,680,000 | N/A | 61,680,000 | 100% | Completed | N/A | N/A | N/A
94 | AINEBYOONA ERIC | 360 GABION BOXES OF (2X1X1) INSTALLATION AT THE FOOTBALL PITCH AND LINK ROAD 7 INCLUDING TRANSPORTATION OF HARD CORE FROM NYABIHOKO | 42,000,000 | 0 |  | 80% | Completed | N/A | Nil | Nil
95 | AINEBYOONA ERIC | 275 GABION BOXES OF (2X1X1) INSTALLATION NEAR DRY MILL AND SILO INCLUDING TRANSPORTATION OF HARD CORE FROM NYABIHOKO | 32,940,000 | N/A |  | 100% | Completed | N/A | Nil | Nil
96 | AINEBYOONA ERIC | PROPOSED Retaining WALL AT THE MAIN GATE (60MX2.3M) | 25,000,000 | N/A | 25,000,000 | 100% | Completed | N/A | Nil | Nil
97 | AINEBYOONA ERIC | STONE PITCHING FOR THE DRAINAGE CHANNEL AT THE MOSQUE | 36,000,000 | N/A | - | 40% | Halted | N/A | N/A | NIL
98 | INSPIRE | BLOCK MAKING MACHINE |  | 0 |  | 60% | Ongoing | machine maintenance and repair | produced 4674 blocks | machine needs overall maintenance and repair | stone chips and cement |  | production of 18000 blocks
99 | NUATU | STONE CRUSHER |  |  |  | 70% | Ongoing | STEEL WORKS FOR THE RETAINING WALL | CASTING OF STRIP FOUNDATION PADS AND COLUMNS | DELAY OF MATERIALS | EMBEDDED PLATS | JULY | INSTALLUTION OF MACHINE CRUSHER
100 | NEWELL TECHNOLOGIES | Booster tanks |  |  |  | 35% | Ongoing | Curing the tank slabs | casting slabs | DELAY OF MATERIALS | procurement of bricks rate should be revised | 20th june 2026 | Walling, steelwork and finishes
101 | NEWELL TECHNOLOGIES | Generator and Guard house |  |  |  | 55% | Ongoing | construction of the splash apron | Brick workup to the wallplate | Delay of materials | increased speed in material delivery | 20th june 2026 | Roofing,plastering and painting
102 | NEWELL TECHNOLOGIES | Toilet |  |  |  | 40% | Ongoing | Plastering of the sub structure | Brick work up to the slab level, plastering | Delay of materials | increased speed in material delivery | 20/06/2026 | slab casting, walling and roofing
103 | NEWELL TECHNOLOGIES | Stone pitching |  |  |  | 0% | Not Started | Nil | Nil | Nil | increased speed in material delivery | 20/06/2026 | retaining wall construction
104 | NEWELL TECHNOLOGIES | fencing |  |  |  | 0% | Not Started | Nil | Nil | Nil | increased speed in material delivery | 20/06/2026 | Fencing
105 | NEWELL TECHNOLOGIES | Booster pump house |  |  |  | 0% | Not Started | Nil | Nil | Nil | increased speed in material delivery | 20/06/2026 | Brickwork and finishes
106 | NEWELL TECHNOLOGIES | Intake chamber. |  |  |  | 5% | Halted | Nil | Nil | demobilisation of an excavator from the site before finishing excavation | Machinery controlled should be given to the contractor when working on his site | 20/06/2026 | Casting slabs and walls
107 | NEWELL TECHNOLOGIES | weir |  |  |  | 0% | Not Started | Nil | Nil | delay of diversion of the river | An excavator to be given enough time to divert the river |  | Diversion of the river and construction of the weir
108 | NEWELL TECHNOLOGIES | Generator and pump house |  |  |  | 0% | Not Started | Nil | Nil | Nil | increased speed in material delivery | 20/06/2026 | Brickwork and finishes
109 | JAMES | Excavation/ trenching |  |  |  | 70% | Ongoing | Trenching in kabuhungu hill | Trenching along kahengye Kakiika road. | Delay of equipment like backhoe and highup vehicle | dedicate more days for the back hoe to work in water project | 20th july 2026 | Finishing excavation
110 | JAMES | Laying of the pipes |  |  |  | 65% | Ongoing | Laying of the pipes | Laying and backfilling of pipes along kahengye Kakiika road. | Delay of equipment like backhoe and highup vehicle | dedicate more days for the back hoe to work in water project | 20th july 2026 | Finishing laying of pipes and pressure testing
111 | MAKOONA | contract 1 1) 2 warehouse storage 2)Wet mill 3) Dry mill 4)cosmetics , Holding area at packagining , Evaporator , Extraction , Boiler , spray dry & canteen | 170,000,000 | 0 | 170,000,000 | 100% | Completed | [5 empty] | 1) IAG
112 | MAKOONA | contract 2 1) Evaporator staircase 2) Dismantling main gate 3) Steam line support 4) stand tank at boiler 5) Top up of gas cutting | 22,000,000 | 0 | 22,000,000 | 100% | Completed | Nil | Nil | Nil
113 | MAKOONA | contract 3 1) 2 roller shutter for the power house 2) Fabrication of the gate at extraction 3) Extension of the roof at freeze dry | 21,000,000 |  | 21,000,000 | 100% | Completed | Finishing works | Nil | Nil
114 | MAKOONA | Nyabihoko project & spent tank | 47,500,000 |  | 47,500,000 | 100% | Completed | Nil | Nil | Nil
115 | MAKOONA | contract 5 1) silos 2) pitch 3) door at guest house | 15,500,000 | 0 | 15,500,000 | 100% | Completed
116 | MAKOONA | Wood shed 1 | 65,000,000 | 0 | 20,000,000 | 50% | Halted | Nil | Nil | Nil | 15.06.2026 | 1.06.2026 | 1) Inspire
117 | MAKOONA | wood shed 2 | 65,000,000 |  | 25,000,000 | 70% | Halted | Finishing works | Nil | Nil | 10.06.2026 | 1.06.2026 | 1) Inspire
118 | MAKOONA | Re-roofing at admin block | 10,000,000 |  | 10,000,000 | 100% | Completed | Nil | Nil | Nil
119 | MAKOONA | Fabrication of admin platform and dismantling , frames and flag tower | 2,500,000 | 0 | 2,500,000 | 100% | Completed
120 | MAKOONA | Fabrication of two billboards | 10,000,000 | 0 | 10,000,000 | 100% | Completed | Nil | Nil | Nil
121 | MAKOONA | Fabrication , installing ,supplying the fixing bolts for flags & flyers | 10,000,000 |  | 10,000,000 | 100% | Completed | Nil | Nil | Nil
122 | MAKOONA | Fabrication and roofing at husk house | 25,000,000 | 0 | 5,000,000 | 80% | Halted |  |  |  | 07.06.2026 | 1.06.2026 | 1) Inspire
123 | MAKOONA | Fabrication of bases for the foundation of dryer at nyabihoko | 2,500,000 | 0 | 2,500,000 | 100% | Completed | Nil | Nil | Nil
124 | MAKOONA | NEW CONTRACTS
125 | MAKOONA | Cement store | 60,000,000 |  | 0 | 0% | Not Started | Nil | Nil | Nil | 20.06.2026 | 1.06.2028 | 1) Inspire
126 | MAKOONA | Residential House | 16,667,000 |  | 0 | 0% | Not Started | Nil | Nil | Nil | 15.06.2026 | 1.06.2028 | 1) Inspire
127 | MAKOONA | Construction offices | 4,445,000 |  | 0 | 0% | Halted | Nil | Nil | Nil | 15.06.2026 | 1.06.2028 | 1) Inspire
128 | MAKOONA | Dinning house | 17,850,000 |  | 0 | 60% | Halted | Nil | Nil | Nil | 15.06.2026 | 1.06.2028 | 1) Inspire
129 | MAKOONA | Agricultural offices | 4,450,000 |  | 0 | 0% | Halted | Nil | Nil | Nil | 15.06.2026 | 1.06.2028 | 1) Inspire
130 | MAKOONA | Kitchen | 6,000,000 |  | 0 | 0% | Not Started | Nil | Nil | Nil | 15.06.2026 | 1.06.2028 | 1) Inspire
131 | NOWERA | Freeze dry |  |  |  | 65% | halted | Nil | Nil | financial support | halted project |  | 1) complete blockwork 2) plastering and rendering 3)complete roofing works 4)M&E WORKS
132 | NOWERA | Abbatoir |  |  |  | 52% | Halted | Nil | Nil | financial support | halted project |  | 1) plastering 2) rendering 3) roofing 4)M&E WORKS
133 | NOWERA | Fertilizer shade |  |  |  | 75% | ongoing | steelworks, formwork and casting for the top beam | 1)external blockwork 90% | Nil | 1) accelerate work to improve out put |  | 1) steel works, casting of top beams for both structures 2)plastering and rendering 3)construction of louvres at the fermentation shade
134 | NOWERA | retaining walls |  |  |  | 65% | ongoing | steelworks and formworks for the beam to the retaining wall at fertilizer shade | Nil | low workmanship | 1) speed up work |  | 1) casting of the intermediate beam 2) continued stone pitching 3) casting the top beam 4)coping
135 | NOWERA | capsules and A-shaped units |  |  |  | 54% | ongoing | roof finishes at capsulesfor unit 9 | completed roof finishes for unit 6,7,8 | low workmanship and inadequate tools like silicon guns and hand drills | 1) approval of the variation at the A-Shaped units |  | 1) complete all roof finishes 2) finish all glass installations 3) installing floor tiles 4)M&E WORKS
136 | BAM | Academy |  |  |  |  | ongoing | Ground & Firsts Floors (Slab works, columns, beams, Retaining walls etc. ) | First floor slab 70% Columns for the First Floor | 1) Materials supply 2) Structural and M&E drawings challenges 3) Contractual document availability 4) Low work force and recycling of labour | 1)Enhance and expedite 2) Consultant to expedite their availability to avoid Reworks 3)Updated contractual documents to be availed 4Mobilise more labourers | 30.9.26 | 1) Shell completion 2) Walling commencement and plastering
137 | BAM | Convention |  |  |  |  | ongoing | Retaining walls Columns Water proofing | Earth works Retaining walls 15% Mini convention drawings | 1) Materials supply 2) Structural and M&E drawings challenges 3) Contractual document availability 4)Equipment Availability 5) Low work force and Recycling of Labour | 1)Enhance and expedite 2) Consultant to expedite their availability to avoid Reworks 3)Updated contractual documents to be availed 4)Inspire to work on internal planning for equipment | 28.2.27 | 1) Completion of the Retaining walls 2) Water proofing and Backfilling 3) Structural Drawings completion
138 | BAM | Dispatch Retaining walls |  |  |  |  | ongoing | Retaining walls | First floor slab 70% Columns for the First Floor | 1) Materials supply 2) Structural and M&E drawings challenges 3) Contractual document availability | 1)Enhance and expedite 2) Consultant to expedite their availability to avoid Reworks 3)Updated contractual documents to be availed | 30.9.28 | 1) Shell completion 2) Walling commencement and plastering
139 | BAM | Academy |  |  |  |  | ongoing | Ground & Firsts Floors (Slab works, columns, beams, Retaining walls etc. ) | First floor slab 70% Columns for the First Floor | 1) Materials supply 2) Structural and M&E drawings challenges 3) Contractual document availability | 1)Enhance and expedite 2) Consultant to expedite their availability to avoid Reworks 3)Updated contractual documents to be availed | 30.9.29 | 1) Shell completion 2) Walling commencement and plastering
2 | BAM | Cargolift | - | - | - | 30% | Ongoing | Retaining Wall | - Casting of walls - Casting of staircases | 1. Low workforce 2. Delayed material supply 3. Delays 4. Lack of complete structural drawings | 1. Complete set of drawings to be completed 2. Contractor to do housekeeping at the working area 3)Increase on Manpower | 30-Jun-2026 | Completion of the structure
3 | BAM | Pavilion Works | - | - | - | 2% | Ongoing | Hardcore placing in the substructure | - Completion of earthworks - Commencement of substructure works | 1. Equipment availability 2. Material availability 3. Low manpower 4. Lack of complete set of drawings | 1. Inspire to avail materials and equipment on time 2. Structural & architectural designer to avail drawings on time 3. BAM to increase manpower | 30-Sep-2026 | Completion of the substructure
4 | Inspire | Construction of a Runway | - | - | - | 10% | Ongoing | 1. Cut and fill for the runway 2. Excavation for the drainage system | - Geotextile and rock fill at the airstrip runway plus geogrids - Cut and fill for the airstrip runway - Rock stockpiling at Stavide Stone Quarry - Stockpiling G3 material for fill at the runway - Completion of the design for the runway | 1. Weather-related challenges affecting movement of equipment 2. Continuous breakdown of equipment 3. Lack of petty cash on-site | 1. Stockpiling of materials to curb weather challenges 2. Establish an in-house mechanical team and servicing centre to manage trucks and equipment 3. Avail a service/recovery truck on site | 30-Jun-2027 | 1. Placement of geotextile and geogrids 2. Hardcore placing 3. Stockpiling of fill material 4. Cut and fill for the runway to completion 5. Commencement of drainage structure works 6. Completion of the designs
5 | Sate Builders | Proposed Lakeside Resort Hotel | 556000000 | - | 73000000 | 3% | Ongoing | Excavation for footings Geotechnical investigation Blinding, steel works and RC works | Excavation works Mobilisation | 1) Incomplete designs (Unsatisfactory Structural design) 2) Producing drawings without a geotechnical investigation report given the site challenges 3) Delay in complying to the consultants requirements | 1) Completion of the designs 2) Expediting the geotechnical reports 3) Contractor to do speedy responses to consultants demand | 2026-08-30 | 1)Shell completion

## Work Programme
INSPIRE AFRICA GROUP – CONSTRUCTION DEPARTMENT ¦ WORK PROGRAMME
MAY 2026 STATUS ¦ Prepared by: Construction Department ¦ Date: June 2026
S/N | Contractor | Project Details | Progress (%) | Proposed Commencement / Resumption Date | Proposed Completion Date | Duration (Days/Estimate) | Challenges | Interventions Required | Responsible Person for Intervention | Target Date for Intervention
1 | Matovu Engineering Engineering Services | Perimeter wall and branch off gate to Exhibition | 95% | with in 5 days after commencement | with in 5 days after commencement | with in 5 days after commencement | 1) Soft sand supply and bad weather 2) Traffic control at branch off gate during finishing 3) Delayed payments | 1) Payment 2) Delivery of required material | Finance / Management | with in 5 days after commencement
2 | Matovu Engineering Engineering Services | Main Gate and LHS perimeter wall | 85% | 10 days after disbursement of funds | 10 days after disbursement of funds | 10 days after disbursement of funds | 1) Indecision of finishing details by consultants 2)Delayed payments and bad weather, lack of silt free soft sand for finishes | 1) Payments 2)Remobilisation of workers | Finance / Management | 10 days after disbursement of funds
3 | Matovu Engineering Engineering Services | Concrete Road Paving at Exhibition (Phase 1) | 100% | Completed |  | TBD | 1) Delayed material delivery and inconsistent in water supply |  | Procurement / Site Manager | N/A
4 | Matovu Engineering Engineering Services | Rc Shear wall at Exhibition | 95% | Upon payment / material delivery |  | TBD | Delayed installation of facing bricks to pave way for top coping |  | Site Engineer | 2 weeks from date
5 | Matovu Engineering Engineering Services | Drainage System (Culverts and manholes) | 100% | Completed |  | TBD | Bad weather ( Rainy season) |  | Site Engineer | N/A
6 | Matovu Engineering Engineering Services | Kerb stone installation at football pitch | 100% | Completed |  | TBD | Material supply and delayed payments |  | Finance / Management | N/A
7 | Matovu Engineering Engineering Services | Branch-off gate and perimeter Wall Extension at Steel yard | 73% | Upon payment / material delivery |  | TBD | Delayed structural drawings and design from client |  | Consulting Engineers / PM | 2 weeks from date
8 | Matovu Engineering Engineering Services | Perimeter wall Extension to Chain link | 97% | TBD – awaiting instruction |  | TBD | wall was running within the line of culverts |  | Site Engineer | 2 weeks from date
9 | Matovu Engineering Engineering Services | Concrete Road paving Extension( Phase 2) | 100% | Completed |  | TBD | Levels |  | Site Engineer | N/A
10 | Matovu Engineering Engineering Services | stone pitched retaining wall( Entrance to Exhibition) | 100% | Completed |  | TBD | Indecision on levels by the consulting team |  | Site Engineer | N/A
11 | Matovu Engineering Engineering Services | Kerb Stone installation ( Main road) | 100% | Completed |  | TBD | Delayed kerb delivery |  | Site Engineer | N/A
12 | Matovu Engineering Engineering Services | Walkway Paver laying ( Main road) | 100% | Completed |  | TBD | Bad weather |  | Site Engineer | N/A
13 | Matovu Engineering Engineering Services | Concrete Gutter Casting ( Main road) | 100% | Completed |  | TBD | Indecision on the proper design of the gutter |  | Consulting Engineers / PM | N/A
14 | Matovu Engineering Engineering Services | Storage tent platform | 96% | TBD – awaiting instruction |  | TBD | Stocking of material on the platform |  | Procurement / Site Manager | 2 weeks from date
15 | Matovu Engineering Engineering Services | 2 Gates and perimeter wall construction from main gate to drymill | 20% | Upon payment / material delivery |  | TBD | lack of hardcore and solid blocks |  | Site Engineer | 2 weeks from date
16 | Matovu Engineering Engineering Services | Chain link Enclosure at Steel yard | 87% | TBD – awaiting instruction |  | TBD | Bad weather |  | Site Engineer | 2 weeks from date
17 | Matovu Engineering Engineering Services | Stone pitched retaining wall at storage tent | 42% | Ongoing |  | TBD | Hard core delivery |  | Site Engineer | 2 weeks from date
18 | Matovu Engineering Engineering Services | Raisers and Separation Wall in Exhibition | 100% | Completed |  | TBD | indecision on the design |  | Consulting Engineers / PM | N/A
19 | Matovu Engineering Engineering Services | Modern toilets, Kitchen and Washrooms at storage tent | 10% | Upon payment / material delivery |  | TBD | Drawings |  | Consulting Engineers / PM | 2 weeks from date
20 | Matovu Engineering Engineering Services | Retaining wall btn Exhibition and Storage tent | 0% | TBD |  | TBD | Hardcore delivery |  | Site Engineer | 2 weeks from date
21 | Matovu Engineering Engineering Services | Courtyard Lantern installation at selected parts around Exhibition roads | 15% | Upon payment / material delivery |  | TBD | Un delivered lanterns |  | Site Engineer | 2 weeks from date
22 | Matovu Engineering Engineering Services | Residential units construction at white house | 25% | Ongoing |  | TBD | Shared Retaining wall with the cement storage ( residentials have to wait) |  | Site Engineer | 2 weeks from date
23 | Matovu Engineering Engineering Services | Consultancy offices at white house | 78% | Ongoing |  | TBD | Irregular supply of blocks due to consistent machine break down |  | Equipment Manager | 2 weeks from date
24 | Matovu Engineering Engineering Services | Agricultural offices at white house | 41% | Ongoing |  | TBD | Blocks |  | Site Engineer | 2 weeks from date
25 | Matovu Engineering Engineering Services | Dinning facility at white house | 92% | Ongoing |  | TBD | Lack of clean silt free soft sand |  | Site Engineer | 2 weeks from date
26 | Matovu Engineering Engineering Services | Security house | 0% | TBD |  | TBD | UETCL planted a pole within the house location |  | Site Engineer | 2 weeks from date
27 | Matovu Engineering Engineering Services | Cement Store facility down at white house | 39% | TBD – awaiting instruction |  | TBD | Machine to spread soil in preparation for oversite concrete |  | Equipment Manager | 2 weeks from date
28 | Matovu Engineering Engineering Services | Extension of dining facility at white house | 0% | TBD |  | TBD | Delayed payments to add on man power |  | Finance / Management | 2 weeks from date
29 | Matovu Engineering Engineering Services | Storm water trench at Exhibition | 40% | TBD – awaiting instruction |  | TBD | payments |  | Finance / Management | 2 weeks from date
30 | DOASCORE | Construction of a dancing fountain | 100% | Completed |  | TBD |  | 1) IPC Payment 10M | Project Manager / Site Engineer | N/A
31 | DOASCORE | Tilling of the fountain | 100% | Completed |  | TBD | 1) Indecision of finishing details 2)Indecision on the gate design | 1. IPC payment 17,550,000 | Finance / Management | N/A
32 | DOASCORE | Fountain control room | 94% | 10.06.2026 | 10.06.2026 | 10.06.2026 | 1) Delayed payments | 1) IPC payment 12M | Finance / Management | 10.06.2026
33 | DOASCORE | Cattle shade 1 Nyabihoko | 60% | 15.06.2026 | 15.06.2026 | 15.06.2026 | 1} Delayed delivery of materials on site | 1) IPC Payment 16M | Finance / Management | 15.06.2026
34 | SIGI PATRICK | Main gate, Gate to the pitch and Gate to the Administration block | 70% | Ongoing | 8 days after getting materials | 8 days after getting materials | 1) lack of materials 2) lack of money to pay workers |  | Procurement / Site Manager | 8 days after getting materials
35 | SIGI PATRICK | Staff houses 5 rooms | 99% | Completed |  | TBD | Delayed to pay balance | Paying balance | Project Manager / Site Engineer | N/A
36 | SIGI PATRICK | View point and freeze dry gate | 80% | Ongoing | 10 days after getting materials | 10 days after getting materials | 1) Indecision on coping design | 1) Coping Design details | Consulting Engineers / PM | 10 days after getting materials
37 | SIGI PATRICK | Dry mill and wet mill light | 85% | 7 days after getting materials | 7 days after getting materials | 7 days after getting materials | 1) lack of materials 2) lack of money to pay workers |  | Procurement / Site Manager | 7 days after getting materials
38 | SIGI PATRICK | Packaging light, roastry basement light and extraction | 80% | 14 after getting materials | 14 after getting materials | 14 after getting materials | 1) lack of materials 2) lack of money to pay workers |  | Procurement / Site Manager | 14 after getting materials
39 | SIGI PATRICK | Museum | 99% | Completed | 0 | 0 | Waiting for balance |  | Site Engineer | N/A
40 | SIGI PATRICK | White house/Kawiri's house | 95% | Completed | 1 day | 1 day | Waiting for balance |  | Site Engineer | N/A
41 | SIGI PATRICK | Slab piping of wood shade |  | Completed | 0 | 0 | Waiting for money |  | Site Engineer | N/A
42 | SIGI PATRICK | Slab piping of dry mill basement |  | Completed | 0 | 0 | Waiting for money |  | Site Engineer | N/A
43 | SIGI PATRICK | Lower cave and upper cave cottages | 65% | Ongoing | 60 days | 60 days | 1) lack of materials 2) lack of money to pay workers |  | Procurement / Site Manager | 60 days
44 | SIGI PATRICK | Exhibition tent wiring and 16 sign posts at the pitch | 65% | Ongoing | 14 days | 14 days | 1) lack of materials 2) lack of money to pay workers |  | Procurement / Site Manager | 14 days
45 | SIGI PATRICK | Administration block | 90% | Upon payment / material delivery |  | TBD | 1) lack of materials 2) lack of money to pay workers |  | Procurement / Site Manager | 2 weeks from date
46 | SIGI PATRICK | Addition works in lower and upper cave cottages | 0% | 90 days | 90 days | 90 days | 1) lack of materials 2) lack of money to pay workers |  | Procurement / Site Manager | 90 days
47 | ALEX MATWA | Cosmetic | 60% | Ongoing | 15/06/2026 | 15/06/2026 | change of design, delay of materials, transports material for himself | aggregates,sand,and blocks(0.2x0.4)cm3 | Procurement / Site Manager | 15/06/2026
48 | ALEX MATWA | LPG(tank base) | 85% | 15/06/2026 | 15/06/2026 | 15/06/2026 | money, material | sand, aggregates | Procurement / Site Manager | 15/06/2026
49 | ALEX MATWA | ramp behind cold brew | 85% | 20/06/2026 | 20/06/2026 | 20/06/2026 | Money and material | sand and aggregates | Procurement / Site Manager | 20/06/2026
50 | ALEX MATWA | Boiler chamber | 100% | Completed |  | TBD | money demand |  | Site Engineer | N/A
51 | ALEX MATWA | PARTION WALL INSIDE COSMETICS | 100% | Completed |  | TBD | money demand |  | Site Engineer | N/A
52 | ALEX MATWA | POWER HOUSE AT THE DAM AREA | 100% | Completed |  | TBD | money demand |  | Site Engineer | N/A
53 | ALEX MATWA | Stone pitching behind cosmetics | 100% | Completed |  | TBD | money demand |  | Site Engineer | N/A
54 | ALEX MATWA | Retaining wall behind power house | 100% | Completed |  | TBD | money demand |  | Site Engineer | N/A
55 | MORIS | Cosmetics roofing and fabrication | 20% | Upon payment / material delivery |  | TBD | completion of slab |  | Site Engineer | 2 weeks from date
56 | MORIS | POWER HOUSE | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
57 | MORIS | EXHIBITION TENT | 94% | Ongoing |  | TBD | 1) Delayed payments | sealant | Finance / Management | 2 weeks from date
58 | PETER SEGAWA | Casting topslab at the power house | 50% | Ongoing |  | TBD | money, material | sand, aggregates | Procurement / Site Manager | 2 weeks from date
59 | PETER SEGAWA | Drainage channel behind Extraction | 40% | Ongoing |  | TBD | material and money |  | Procurement / Site Manager | 2 weeks from date
60 | PETER SEGAWA | required to determine levels | 50% | Upon payment / material delivery |  | TBD | change in levels |  | Site Engineer | 2 weeks from date
61 | TASHOBYA WENS | Construction of the gates | 70% | Ongoing | 25.06.2026 | 25.06.2026 | 1) delays in material delivery (2) Delayed payments | 1) IPC Payment 1M 2) Approval of the Variation | Finance / Management | 25.06.2026
62 | TASHOBYA WENS | retaining wall, car ramp, perimeter wall |  | Ongoing |  | TBD |  |  | Site Engineer | 2 weeks from date
63 | TASHOBYA WENS | CAR parking,perimeter wall and kerbstone | 80% | Ongoing | 15.06.2026 | 15.06.2026 | 1) Indecision of finishing details | 1) Finishing details 2)Partial payment | Finance / Management | 15.06.2026
64 | TASHOBYA WENS | construction of stone masonry drai,culvert installation and pavement | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
65 | MAURICE | Power House/Mezzanine Floor | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
66 | MAURICE | Exhibition Works | 90% | Ongoing | 10.06.2026 | 10.06.2026 | 1)Payments delay | 1) passage tent need to be checked and approved before we proceed | Finance / Management | 10.06.2026
67 | MAURICE | Cosmetic Modification | 30% | Upon payment / material delivery |  | TBD | 1)Works were halted due to safety precautions that were instructed by the project manager | 1) Resumption of works | Project Manager | 2 weeks from date
68 | ASIIMWE (MWIMO) | CONSTRUCTION OF RETAINING WALL | 95% | Ongoing |  | TBD | WATER TREATMENT 95% | 05.06.2026 | Project Manager / Site Engineer | 2 weeks from date
69 | ASIIMWE (MWIMO) | CONSTRUCTION OF WETMILL |  | Ongoing |  | TBD |  |  | Site Engineer | 2 weeks from date
70 | PTAKA | construction of retaining wall and repairing the storm water drainage channel at link 1 & link 7 roads | 70% | Ongoing | 30.06.2026 | 30.06.2026 | 1) inadequate labour 2) material (hardcore) 3) Delayed payments | payment | Finance / Management | 30.06.2026
71 | PTAKA | Concrete U drain, access culverts and end structures for cross Culvert at link 7 | 50% | Ongoing | 15.06.2026 | 15.06.2026 | delayed payments | payments | Finance / Management | 15.06.2026
72 | OCHAYA | Installation of the curtain wall at exhibition tent | 95% | Ongoing |  | TBD | plumbing works to help in work progress | 1) IPC Payment | Finance / Management | Immediate / 1 week
73 | OCHAYA | Administration gate cladding works | 100% | Completed |  | TBD | IPC payment |  | Finance / Management | N/A
74 | OCHAYA | Store 1 cladding works. | 85% | Ongoing |  | TBD | ,IPC payment |  | Finance / Management | 2 weeks from date
75 | OCHAYA | packaging cladding works and glass partition | 100% | Completed |  | TBD | IPC payment |  | Finance / Management | N/A
76 | OCHAYA | Cosmetics cladding | 85% | Ongoing |  | TBD | IPC payment |  | Finance / Management | 2 weeks from date
77 | OCHAYA | Roastrty Lab area glass roof | 100% | Completed |  | TBD | ,IPC payment |  | Finance / Management | N/A
78 | OCHAYA | canopy front roastry | 100% | Completed |  | TBD | ,IPC payment |  | Finance / Management | N/A
79 | OCHAYA | Cladding inside the roastry | 100% | Completed |  | TBD | IPC payment |  | Finance / Management | N/A
80 | OCHAYA | cladding and glass partition coffee shop | 100% | Completed |  | TBD | IPC payment |  | Finance / Management | N/A
81 | OCHAYA | Cladding for the fountain power house | 95% | Upon payment / material delivery |  | TBD | IPC payment |  | Finance / Management | 2 weeks from date
82 | OCHAYA | Office block and wetmill cladding | 98% | Upon payment / material delivery |  | TBD | IPC payment |  | Finance / Management | 2 weeks from date
83 | OCHAYA | Freeze dry ramp cladding | 0% | TBD |  | TBD | IPC payment |  | Finance / Management | 2 weeks from date
84 | KAZORA ENGINEERING | Stone masonry work below link 2 below dispatch. 3000m | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
85 | KAZORA ENGINEERING | Finishing masonry wall(stone pointing) | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
86 | KAZORA ENGINEERING | Fixing culvertsand casting 3 manholes near cement store. | 85% | Ongoing | 14/06/2026 | 14/06/2026 | adequate murram,IPC payment |  | Finance / Management | 14/06/2026
87 | KAZORA ENGINEERING | Building edges ,store leveling,fixing culverts,casting edges with retaining wall(CEO residence) | 75% | 20/06/2026 | 20/06/2026 | 20/06/2026 | culverts,IPC payment |  | Finance / Management | 20/06/2026
88 | KAZORA ENGINEERING | Fixing culverts and 4 manhole covers in NYABIHOKO | 60% | 28/06/2026 | 28/06/2026 | 28/06/2026 | missing culverts,aggregate,sand |  | Site Engineer | 28/06/2026
89 | KAZORA ENGINEERING | Stone pitching and curbstones,near cement store. | 15% | 20/07/2026 | 20/07/2026 | 20/07/2026 | hardcore,IPC payment |  | Finance / Management | 20/07/2026
90 | JOSIRA ENGINEERING SERVICES. | Construction of concrete U drain at ring road 1 (375m) | 90% | Ongoing | 2nd June 2026 | 2nd June 2026 | Delayed payments, Delay in material delivery | 1) IPC Payment of 60M | Finance / Management | 2nd June 2026
91 | JOSIRA ENGINEERING SERVICES. | Stone pitching U drain from academy to Helipad road(305m) | 60% | TBD – awaiting instruction | 17th June 2026 | 17th June 2026 | Delayed material supply of hard core |  | Procurement / Site Manager | 17th June 2026
92 | JOSIRA ENGINEERING SERVICES. | Construction of concrete drainage at left hand side and stone pitching drainage at right hand side at CEO road | 12% | TBD – awaiting instruction | 2nd July 2026 | 2nd July 2026 | 1) Delayed payments |  | Finance / Management | 2nd July 2026
93 | AINEBYOONA ERIC | 514 GABION BOXES OF (2X1X1) INSTALLATION AT THE TANK HILL INCLUDING TRANSPORTATION OF HARD CORE FROM NYABIHOKO | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
94 | AINEBYOONA ERIC | 360 GABION BOXES OF (2X1X1) INSTALLATION AT THE FOOTBALL PITCH AND LINK ROAD 7 INCLUDING TRANSPORTATION OF HARD CORE FROM NYABIHOKO | 80% | Completed |  | TBD |  |  | Site Engineer | N/A
95 | AINEBYOONA ERIC | 275 GABION BOXES OF (2X1X1) INSTALLATION NEAR DRY MILL AND SILO INCLUDING TRANSPORTATION OF HARD CORE FROM NYABIHOKO | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
96 | AINEBYOONA ERIC | PROPOSED Retaining WALL AT THE MAIN GATE (60MX2.3M) | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
97 | AINEBYOONA ERIC | STONE PITCHING FOR THE DRAINAGE CHANNEL AT THE MOSQUE | 40% | Upon payment / material delivery |  | TBD |  |  | Site Engineer | 2 weeks from date
98 | INSPIRE | BLOCK MAKING MACHINE | 60% | Ongoing |  | TBD | machine needs overall maintenance and repair | stone chips and cement | Equipment Manager | 2 weeks from date
99 | NUATU | STONE CRUSHER | 70% | Ongoing | JULY | JULY | DELAY OF MATERIALS | EMBEDDED PLATS | Procurement / Site Manager | JULY
100 | NEWELL TECHNOLOGIES | Booster tanks | 35% | Ongoing | 20th june 2026 | 20th june 2026 | DELAY OF MATERIALS | procurement of bricks rate should be revised | Procurement / Site Manager | 20th june 2026
101 | NEWELL TECHNOLOGIES | Generator and Guard house | 55% | Ongoing | 20th june 2026 | 20th june 2026 | Delay of materials | increased speed in material delivery | Procurement / Site Manager | 20th june 2026
102 | NEWELL TECHNOLOGIES | Toilet | 40% | Ongoing | 20/06/2026 | 20/06/2026 | Delay of materials | increased speed in material delivery | Procurement / Site Manager | 20/06/2026
103 | NEWELL TECHNOLOGIES | Stone pitching | 0% | 20/06/2026 | 20/06/2026 | 20/06/2026 | Nil | increased speed in material delivery | Procurement / Site Manager | 20/06/2026
104 | NEWELL TECHNOLOGIES | fencing | 0% | 20/06/2026 | 20/06/2026 | 20/06/2026 | Nil | increased speed in material delivery | Procurement / Site Manager | 20/06/2026
105 | NEWELL TECHNOLOGIES | Booster pump house | 0% | 20/06/2026 | 20/06/2026 | 20/06/2026 | Nil | increased speed in material delivery | Procurement / Site Manager | 20/06/2026
106 | NEWELL TECHNOLOGIES | Intake chamber. | 5% | 20/06/2026 | 20/06/2026 | 20/06/2026 | demobilisation of an excavator from the site before finishing excavation | Machinery controlled should be given to the contractor when working on his site | Project Manager / Site Engineer | 20/06/2026
107 | NEWELL TECHNOLOGIES | weir | 0% | TBD |  | TBD | delay of diversion of the river | An excavator to be given enough time to divert the river | Project Manager / Site Engineer | 2 weeks from date
108 | NEWELL TECHNOLOGIES | Generator and pump house | 0% | 20/06/2026 | 20/06/2026 | 20/06/2026 | Nil | increased speed in material delivery | Procurement / Site Manager | 20/06/2026
109 | JAMES | Excavation/ trenching | 70% | Ongoing | 20th july 2026 | 20th july 2026 | Delay of equipment like backhoe and highup vehicle | dedicate more days for the back hoe to work in water project | Equipment Manager | 20th july 2026
110 | JAMES | Laying of the pipes | 65% | Ongoing | 20th july 2026 | 20th july 2026 | Delay of equipment like backhoe and highup vehicle | dedicate more days for the back hoe to work in water project | Equipment Manager | 20th july 2026
111 | MAKOONA | contract 1 1) 2 warehouse storage 2)Wet mill 3) Dry mill 4)cosmetics , Holding area at packagining , Evaporator , Extraction , Boiler , spray dry & canteen | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
112 | MAKOONA | contract 2 1) Evaporator staircase 2) Dismantling main gate 3) Steam line support 4) stand tank at boiler 5) Top up of gas cutting | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
113 | MAKOONA | contract 3 1) 2 roller shutter for the power house 2) Fabrication of the gate at extraction 3) Extension of the roof at freeze dry | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
114 | MAKOONA | Nyabihoko project & spent tank | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
115 | MAKOONA | contract 5 1) silos 2) pitch 3) door at guest house | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
116 | MAKOONA | Wood shed 1 | 50% | 1.06.2026 | 1.06.2026 | 1.06.2026 |  | 15.06.2026 | Project Manager / Site Engineer | 1.06.2026
117 | MAKOONA | wood shed 2 | 70% | 1.06.2026 | 1.06.2026 | 1.06.2026 |  | 10.06.2026 | Project Manager / Site Engineer | 1.06.2026
118 | MAKOONA | Re-roofing at admin block | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
119 | MAKOONA | Fabrication of admin platform and dismantling , frames and flag tower | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
120 | MAKOONA | Fabrication of two billboards | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
121 | MAKOONA | Fabrication , installing ,supplying the fixing bolts for flags & flyers | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
122 | MAKOONA | Fabrication and roofing at husk house | 80% | 1.06.2026 | 1.06.2026 | 1.06.2026 |  | 07.06.2026 | Project Manager / Site Engineer | 1.06.2026
123 | MAKOONA | Fabrication of bases for the foundation of dryer at nyabihoko | 100% | Completed |  | TBD |  |  | Site Engineer | N/A
124 | MAKOONA | NEW CONTRACTS |  | Ongoing |  | TBD |  |  | Site Engineer | 2 weeks from date
125 | MAKOONA | Cement store | 0% | 1.06.2028 | 1.06.2028 | 1.06.2028 |  | 20.06.2026 | Project Manager / Site Engineer | 1.06.2028
126 | MAKOONA | Residential House | 0% | 1.06.2028 | 1.06.2028 | 1.06.2028 |  | 15.06.2026 | Project Manager / Site Engineer | 1.06.2028
127 | MAKOONA | Construction offices | 0% | 1.06.2028 | 1.06.2028 | 1.06.2028 |  | 15.06.2026 | Project Manager / Site Engineer | 1.06.2028
128 | MAKOONA | Dinning house | 60% | 1.06.2028 | 1.06.2028 | 1.06.2028 |  | 15.06.2026 | Project Manager / Site Engineer | 1.06.2028
129 | MAKOONA | Agricultural offices | 0% | 1.06.2028 | 1.06.2028 | 1.06.2028 |  | 15.06.2026 | Project Manager / Site Engineer | 1.06.2028
130 | MAKOONA | Kitchen | 0% | 1.06.2028 | 1.06.2028 | 1.06.2028 |  | 15.06.2026 | Project Manager / Site Engineer | 1.06.2028
131 | NOWERA | Freeze dry | 0.65 | Upon payment / material delivery |  | TBD | financial support | halted project | Project Manager / Site Engineer | 2 weeks from date
132 | NOWERA | Abbatoir | 0.52 | Upon payment / material delivery |  | TBD | financial support | halted project | Project Manager / Site Engineer | 2 weeks from date
133 | NOWERA | Fertilizer shade | 0.75 | Ongoing |  | TBD |  | 1) accelerate work to improve out put | Project Manager / Site Engineer | 2 weeks from date
134 | NOWERA | retaining walls | 0.65 | Ongoing |  | TBD | low workmanship | 1) speed up work | Project Manager / Site Engineer | 2 weeks from date
135 | NOWERA | capsules and A-shaped units | 0.54 | Ongoing |  | TBD | low workmanship and inadequate tools like silicon guns and hand drills | 1) approval of the variation at the A-Shaped units | Project Manager / Site Engineer | 2 weeks from date
136 | BAM | Academy (Ground & First Floors – Slab works, columns, beams, retaining walls) | Ongoing | Ongoing | 30-Sep-2026 | TBD | Materials supply; Structural and M&E drawings challenges; Contractual document availability; Low workforce | Enhance and expedite; Consultant to expedite to avoid reworks; Updated contractual documents to be availed; Mobilise more labourers | Consulting Engineers / PM / Site Engineer | 30 Jun 2026
137 | BAM | Convention Centre (Retaining walls, columns, waterproofing) | Ongoing | Ongoing | 28-Feb-2027 | TBD | Materials supply; Structural and M&E drawings challenges; Contractual document availability; Equipment availability; Low workforce | Enhance and expedite; Consultant to expedite; Updated contractual documents; Inspire to plan internal equipment | Consulting Engineers / PM / Site Engineer | 30 Jun 2026
138 | BAM | Dispatch Retaining Walls | Ongoing | Ongoing | 30-Sep-2028 | TBD | Materials supply; Structural and M&E drawings challenges; Contractual document availability | Enhance and expedite; Consultant to expedite; Updated contractual documents | Consulting Engineers / PM / Site Engineer | 30 Jun 2026
139 | BAM | Cargolift (Retaining wall structure) | 30% | Ongoing | 30-Jun-2026 | TBD | Low workforce; Delayed material supply; Lack of complete structural drawings | Complete set of drawings; Contractor to improve site housekeeping; Increase manpower | PM / Site Engineer | 30 Jun 2026
140 | BAM | Pavilion Works (Hardcore placing, substructure) | 2% | Ongoing | 30-Sep-2026 | TBD | Equipment availability; Material availability; Low manpower; Lack of complete set of drawings | Inspire to avail materials and equipment on time; Structural designer to avail drawings; BAM to increase manpower | PM / Site Engineer | 30 Jun 2026
141 | INSPIRE | Construction of a Runway (Cut and fill, drainage excavation) | 10% | Ongoing | 30-Jun-2027 | TBD | Weather-related challenges; Continuous equipment breakdowns; Lack of petty cash on-site | Stockpile materials; Establish in-house mechanical team; Avail service/recovery truck on site | Equipment Manager / PM | 30 Jun 2026
142 | SATE BUILDERS | Proposed Lakeside Resort Hotel (Excavation for footings, geotechnical investigation, blinding, steel works and RC works) | 3% | Ongoing | TBD | TBD | Incomplete designs (unsatisfactory structural design); Producing drawings without geotechnical investigation report; Delays in complying with consultant requirements | Completion of designs; Expediting geotechnical reports; Contractor to provide speedy responses to consultant demands | Consulting Engineers / PM | 30 Jun 2026

## Contractors verified
INSPIRE AFRICA GROUP – VERIFIED CONTRACTORS: VALUE OF WORKS
S/No | Contractor Name | Contract Sum (UGX) | Amount Paid to Date (UGX) | Verified Value Owed (UGX) | Consultant Recommendation | CEO Approval | Remarks
1 | Talemwa Job | 165000000 | 103000000 | 8000000 | 8000000 | 8000000 | Verified Approved for payment bay consultant on 09/05/2026
2 | Matovu Vincent Engineering | 852070000 | 265000000 | 104069430
3 | Asiimwe Emmy - Mwinos | 150000000 | 35000000 | 10040850
4 | Ainebyona Investments | 197620000 | 95000000 | 64188000
5 | Kyambogo Ian Face brick Installation | 22000000 | 13000000 | -8000 |  |  | To be given materials to finish works, Value of works doen is equivalent to amount paid
6 | Arinaitwe David Kazoora | 139500000 | 88000000 | 6408000
7 | Alex Matwa | 79344600 | 40000000 | 14485140
8 | Wambogo Samson | 44000000 | 28000000 | 2989449
9 | Mubajje Sulah | 82250000 | 23000000 | 5067447
24 | Alex Carpenter | 14000000 | 0 | 0
10 | Josira Investments | 130000000 | 30000000 | 17180848
11 | Segawa Peter | 24000000 | 14000000 | 2016000
12 | Omollo Maurice | 375600000 | 140000000 | 9508495.6795
| TOTAL | 2275384600 | 874000000 | 243945659.6795 | 8000000 | 8000000

## Consultancy Works
INSPIRE AFRICA GROUP – ENGINEERING & CONSULTANCY WORKS ¦ MAY 2026
Project | Consultant | Planned Progress | Actual Progress | Contract Amount (UGX) | Amount Paid (UGX)
Feasibility study for development of a sewer network and wastewater treatment infrastructure | W.S.T (Dr. Eng. Swaib Semiyaga) | 60% | 50% | 200,000,000 | 60,000,000
Detailed Hydrological Analysis and Hydraulic Design for Storm Water Drainage System for the Coffee Airport | Foldwoc Engineering Company Ltd (Eng. Simon Yiga) | 50% | 18% | 70,000,000 | 28,000,000
Design of a Lakeside Resort at Nyabihoko | Sate Builders Ltd | 100% | 55% | TBU | TBU
Design of Access Road to the Airport | Venture K | 25% | 20% | TBU | TBU
Quantitative Surveying Consultancy | RSU Frank Tebandeke | TBU | TBU | TBU | TBU
Project Scheduling | RSU Frank Tebandeke | TBU | TBU | TBU | TBU